Terms of Reference for consultants

Consultancy required on “Design and provide trainings for youth on inclusion and promotion of diversity”

July 2018

| Service title | Design and provide trainings for youths on inclusion and promotion of diversity |
| --- | --- |
| Location/Country | Albania (Lezha, Korca, Dibra, Berat) |
| Organization | World Vision Albania |
| Time frame duration | August- December 2018 (26 w/day x 2 expert: 2w/d curricula development and 24 w/d training delivered per each expert) |
| Contract start date | August 2018 |
| Deadline for submission of deliverables | Curricula prepared within 17 September 2018 Trainings delivered (including report, evaluation forms) within December 2018 |

Background information

The 3-years action “Increasing Civil Society Organizations’ Capacities for Mainstreaming Rights of People with Disabilities in Albania” is financed by EU. The action is under the implementation by World Vision as lead organization and Albanian Disability Rights Foundation (ADRF) and the Association Defending the Rights for Persons with Disabilities (MEDPAK).

The action aims to support advocacy efforts in monitoring of public policies related to mainstreaming rights of people with disabilities and capacity building for local CSOs and disabled people organizations (DPOs) in the areas of Korca, Berat, Dibra and Lezha.

The action foreseen interventions at three different levels: (a) mobilizes CSOs, PwDs and their communities to engage into networking and advocacy to influence disability policy framework; (b) monitors implementation of National Plan for People with Disabilities (2016-2020) and (c) engages local networks in dialogue with central government on the status of NDAP implementation, creating synergy between the national and grass root level advocacy.

Thus, this action will improve effectiveness of disability policy framework and enhance rights of people with disabilities through strengthening and mobilizing CSO and PwDs as drivers of change. Moreover, it will create new approaches to increase transparency and improve implementation of National Plan for People with Disabilities at local and national level.

Purpose of the Service

One of the activity of work package no 1 is “Mobilize and train youth volunteers to initiate community service projects to benefit People with Disability”. Six days capacity building trainings will be organized for selected youth volunteers in each of the areas Lezhe, Diber, Korce and Berat for 80 participants (20 per each area). The youth will be trained on:

Travelling together (2 days) – training on how to include disabled people on the main road of personal development.

Diversity curricula (IMPACT) (2 days) - this project model is an integrated approach to adolescent engagement that fosters the skills, behaviors and attitudes necessary for improved participation in their communities’ social, civic and economic life.

Community Participation & Engagement (1 day) - training focusing on stakeholder mapping and analysis, analyzing power dynamics in the communities and understanding and exploring community aspects for mobilization. Gender dynamics and issues related to PwD will be covered.

Youth Voluntarism (1 day) - training on the youth ladder of participation, the levels of engaging youth in decision making and youth mobilization steps, processes, tools to nurture and promote youth activism.

For this reason, we are looking for two experts to work in close consultation with project lead partner-WV as follow:

- to design curricula for Travelling together, Diversity curricula, Community Participation & Engagement, Youth Voluntarism (2 w/d for each expert)

- Provide trainings on the above mention topics in 4 project areas (24 w/d per each expert)

Responsibilities of the Contracted Expert (s):

- Prepare Training Module/Curricula

- Prepare pre/posttest for the trainings

- Collect and analyze data from pre-post tests and evaluation form

- Deliver training in Lezha, Berat, Korca and Dibra

- Prepare training report, including analysis, results and raw data of pre-posttests and evaluation forms for the above mention topics

Note:

- All the training modules developed by experts will be shared for consultation and approval prior to training delivery with WV Ministry Quality Department, Programme specialists and Project Manager for quality assurance purpose. Feedback provided is to be included/ reflected in the curricula/training modules

Deliverables

- Capacity building curricula and programme delivered, as per templates provided by the action in the M&E package;

- Report on the capacity building activity in the four areas, including evaluation forms and data analysis produced, as per templates provided by the action in the M&E package. Pre-post tests and evaluation forms will be conducted during the training days to measure level of knowledge gained and level of satisfaction from participants. The data will be analysed and a report inclusive of curricula, findings from the analysis on the level of gained knowledge will be delivered along with recommendations.

- Raw data of pre-post tests and evaluation forms and analysis

Proposal/ Documents and expert criteria required for submission:

- Please submit the following documents:

- An expression of interest for the consultancy, specifying the training topics for which they are applying

- CV highlighting the expertise of the applicant(s) on six days trainings topics

- The consultancy fee (including transport to project areas and per diem) in total including all applicable taxes

- Criteria

- University degree

- Experience working with youth and/or youth organizations

- Previous experience on training youth groups

- Youth Trainers must be at least two years older than the age of youth to be coached

- Excellent communication skills

- Good writing skills in English

Notes related to World Vision Albania Child Protection Policy:

All people working for World Vision Albania and Kosovo, or visiting its programmes are obliged to sign its Child Protection Policy and Behavior Protocols. This policy aims to create a child-safe organizational environment and is based on the principles of the UN CRC and its protocols.

Important note: The contract will be awarded to the winner upon submission of official documents that certify that the full team of the project – including field team – complies with the child protection rules and procedures. The selected applicant will be informed about the required documents before finalization of the contract.

Principles of child protection involve briefly but are not limited to:

- Treat children with respect and dignity

- Listen to children views and opinions

- Inform children parents/legal guardian/s and take a written consent before any interaction with children (this involves special written permission when it comes to photographs/videos)

- Be sensitive to the child age and maturity, cultural background and local social and family norms and respect them

- Dress in culturally appropriate way.

- Always be in the company of another adult (preferably parent/legal guardian or teacher) when meeting a child

- All visitors to WVA projects must be in accompany of WVA staff.

- Do not abuse with children (sexual, emotional, psychological and physical abuse).

*Please note that World Vision Albania personnel and visitors are expected to report any suspicions of child abuse to the National Director immediately. WVA has policy and procedures that respond to accusations, which allows for a process that respects all involved. World Vision Albania holds the position that adults are always responsible for their behavior with a child, even if a child is acting seductively.

Application procedure:

Questions/requests should be made to the following World Vision address:

Rudina_lula@wvi.org

The deadline for submission of applications is 18 July 2018, Hrs. 17:00. Applications should be sent in a sealed envelope or can be sent by e-mail to the following addresses:

World Vision Albania

Rr. Skenderbej, Ndertesa Gurten, Kati 2, Tirana, Albania

E-mail: Procurment_Albania@wvi.org

https://www.wvi.org/albania

Use WV template as per M&E package

The accommodation of experts will be cover by this project, while the transport in the project areas should be covered by experts