Terms of Reference for External Consultant/s

Training on Professional Crafts, Local Products and Entrepreneurship Skills

| Title | Provision of consultancy services for the design, delivery and mentoring of practical training for artisans and local producers (Albania — Lezha & Kurbin areas). |
| --- | --- |
| Location/Country | Albania/ Lezhe and Kurbin municipalities |
| Organization | World Vision Albania |
| Time frame duration | February 2026-September 2026 |
| Contract start date | February 5, 2026 |
| Deadlines for submission of deliverables | As defined in the following deliverables timeframe |

Background information

World Vision Albania, a branch of the global humanitarian organization World Vision International, has been dedicated to improving the lives of children and communities in Albania since 1999. Our mission focuses on economic development, youth participation, child protection, education, health, and emergency response. In the framework of this project, World Vision Albania aims to improve labor market orientation and access to increase employment and self-employment skills of youth, women, and long-term unemployed individuals in Albania.

The project "Boosting Decent Employment for Youth and Unemployed People in the Cross-border Area of Montenegro and Albania", funded by the European Union through the IPA CBC Cross-Border Cooperation Programme Montenegro-Albania 2014-2020, aims to improve labor market orientation and access, thereby increasing employment and self-employment skills among youth, women, and long-term unemployed individuals in Albania and Montenegro. This project is implemented in partnership with the Employment Agency of Montenegro and National Agency for Employment and Skills in Albania.

The project supports practical skills development (crafts and local product processing), entrepreneurship training, mentoring and linkages with the local private sector to increase market-readiness and formalization of small businesses.

This consultancy will focus on practical, on-the-job training for artisans and local producers, entrepreneurship/business plan development and mentoring support to move selected participants toward viable self-employment and employment pathways.

Purpose of the Service

To engage an external consultant or a small consultancy team to design and deliver a set of practical, competency-based trainings and follow-up mentoring in Albania that will:

- build professional craft and product-processing skills among targeted artisans and producers;

- strengthen entrepreneurship and business planning competencies to enable transition from informal activity to formal micro-enterprises; and

- provide mentoring support to applicants progressing to the self-employment scheme.

All activities must be practice-oriented (learning by doing), gender-sensitive and adapted to the local market context.

Objectives

The consultancy is expected to:

- Design and deliver practical, hands-on training for craft profiles tailored to local artisan traditions and market opportunities in Lezha and Kurbin.

- Design and deliver practical training for local product processors (with emphasis on quality, preservation, packaging and basic marketing practices relevant to local products such as olive/olive oil processing).

- Deliver entrepreneurship and business planning sessions that enable participants to draft practical business plans and prepare for self-employment schemes.

- Provide mentoring support to selected participants to refine business plans and guide them through steps needed for formalisation and market entry.

- Produce timely and complete documentation and reports necessary for project monitoring and donor compliance.

Scope of Work

The consultant(s) will undertake the following task/deliverables:

1. Training on Craft Skills for Artisans (Lezha area)

Objective: To strengthen practical craft skills of women artisans through hands-on training that combines traditional techniques with market-oriented designs.

Target group: Minimum 10 women artisans from rural areas of Lezha (Gjadri, Balldren, Dajç, Blinisht).

Methodology:

- On-the-job training delivered at artisans’ workshops or dedicated training spaces.

- Practical demonstrations, supervised practice and continuous feedback.

- Use of raw materials directly during training sessions.

Working days:

- Trainer: 15 working days (delivery and supervision included).

Key tasks:

- Prepare a practical training plan and daily session outlines.

- Deliver hands-on craft training over 15 training days.

- Integrate elements of traditional crafts with contemporary design and usability.

- Supervise use of raw materials and ensure proper application of techniques.

- Monitor attendance and progress of participants.

Deliverables:

- Approved training agenda and session plans.

- Attendance sheets for all training days.

- Photo documentation of training activities and produced items.

- Short technical report summarising skills gained and recommendations for market application.

Logistics and costs covered:

- Trainer’s professional fee.

- Raw materials required for practical training.

- Organizational costs related to training delivery.

- Participant travel to the training venue (covered by the project).

2. Training for Local Producers (Olive and Olive Oil Processing – Lezha area)

Objective: To enhance technical processing and basic marketing skills of small-scale local producers involved in olive and olive oil processing.

Target group: Minimum 10 women and men local producers from Lezha and surrounding areas.

Methodology:

- On-the-job training delivered directly in processing facilities or appropriate training venues.

- Combination of technical processing sessions and applied marketing guidance.

Working days:

- Trainer 1 (processing expert): 5 working days.

- Trainer 2 (marketing expert): 5 working days.

- Total expert input: 10 working days.

Key tasks:

- Design practical modules on olive/olive oil processing, preservation, bottling and quality control.

- Deliver hands-on demonstrations and supervised practice sessions.

- Provide applied guidance on basic marketing, labeling and market readiness.

- Ensure compliance with basic hygiene and food safety principles.

- Monitor participant engagement and progress.

Deliverables:

- Training agenda and materials for both technical and marketing modules.

- Attendance sheets and.product samples documentation (photos)

- Short report outlining skills acquired, gaps identified and recommendations for improvement.

Logistics and costs covered:

- Trainers’ professional fees.

- Trainers’ travel costs.

- Materials and supplies required for processing demonstrations.

- Organisational costs.

- Participant travel to the training venue (covered by the project).

3. Training on Entrepreneurship and Business Plan Preparation (Lezha and Kurbin areas)

Objective: To equip selected artisans and local producers with practical entrepreneurship and business planning skills in preparation for self-employment opportunities.

Target group: Minimum 12 (preferably 15) artisans and local producers selected from those completing professional skills training in Albania.

Methodology:

- Interactive classroom-based training combined with practical exercises.

- Individual and group work leading to draft business plans.

Working days:

- Business plan trainer: 3 working days (training delivery).

- Trainer/Mentor: 5 working days (coaching and individual support).

- Total expert input: 8 working days.

Key tasks:

- Deliver structured sessions on entrepreneurship fundamentals, costing, pricing and basic financial planning.

- Guide participants through preparation of draft business plans.

- Provide individual coaching and feedback.

- Support participants interested in applying for the self-employment grant scheme.

Deliverables:

- Training materials and business plan templates.

- Attendance sheets and participant evaluations.

- Draft business plans prepared by participants.

- Short training and mentoring report summarising results and recommendations.

Logistics and costs covered:

- Trainers’ and mentor’s professional fees.

- Catering during training days.

- Organisational costs.

- Participant travel to the training venue (covered by the project).

4. Mentoring for Starting New Business Initiatives (Albania)

Objective: To provide structured mentoring support to selected sub-grantees and potential entrepreneurs during the early stages of business start-up and formalisation.

Target group: Selected beneficiaries progressing through the self-employment pathway.

Working days:

- Mentor: 15 working days, spread over a 5-month period.

Key tasks:

- Provide one-to-one and small-group mentoring sessions.

- Guide beneficiaries through administrative, operational and market-entry steps.

- Support refinement of business plans and basic financial projections.

- Track progress and challenges faced by each beneficiary.

Deliverables:

- List of beneficiaries supported and mentoring duration per beneficiary

- Individual mentoring plans and session logs.

- Progress notes for each beneficiary.

- Final mentoring report summarising support provided, outcomes and recommendations for sustainability.

Logistics and costs covered:

- Mentor’s professional fee.

Deliverables and Timeline

The consultant(s) will be contracted for a period of 8  months. Key deliverables include:

| *Deliverable | Details/Milestone | Timeline (deadline) |
| --- | --- | --- |
| Training Preparation | Inception/Training Preparation Package (agenda, detailed module outlines, materials list, logistics plan). | -February 2026 |
| Training delivery and interim documentation: | -Craft training delivery completion and interim report (attendance sheets, photos, short participant assessments). — Deadline: within the training window for craft activities -Local producers training delivery completion and interim report (attendance sheets, photos, product samples documentation). -Entrepreneurship training delivery and interim report (attendance, draft business plans, feedback forms). | -May 2026 |
| Mentoring logs | Mentoring logs and shortlist of candidates recommended for the self-employment scheme (with supporting evidence). — Deadline: at the end of mentoring period. | -July 2026 |
| Final consolidated report | Final consolidated report (English) including: summary of activities, attendance lists, copies of training materials, evaluation results, participant assessments, photos, lessons learned and recommendations for follow-up. — Deadline: within two weeks after completion of the consultancy period.. | September 2026 |

*Note: Please note that the application and final report submitted to World Vision Albania will be prepared and presented in the English language to ensure clarity and consistency in our communications. However, all training sessions, along with associated elements, will be conducted in Albanian. This includes, but is not limited to, the list of participants, presentations, and any supplementary materials. This approach is intended to facilitate better understanding and engagement among local participants, ensuring that the training is accessible and effective.

Responsibilities of WVA

WVA will be responsible for coordination and collaboration required for the implementation of this consultancy. Specifically, WVA will:

- Overall coordination, logistical support and oversight.

- Access to local stakeholders and support in participant identification and selection, in coordination with NAES/RLO.

- Assistance in securing training venues (Career Pro Hub at Kolin Gjoka VET school) and facilitating contacts with local businesses for practical placements or demonstrations.

- Project templates and monitoring tools required for donor reporting.

- Supervision and regular check-ins during implementation.

Reporting and Supervision

The consultant will be responsible for providing updates on progress to WVA (as requested) and provide updates on progress and as per agreement and/or request from the contracting authority. This information will include detailed updates on the training activities, milestones achieved, challenges encountered, and any adjustments made to the training plan. A comprehensive final report will be delivered at the end of the consultancy period.

Supervision will be conducted by WVA to ensure that the training activities are carried out effectively and in alignment with the project's objectives. WVA will oversee the implementation of the training modules, provide feedback, and offer support as needed. Regular check-ins and meetings will be held to discuss progress, address any issues, and ensure that the consultancy is on track to meet its goals. WVA will also facilitate access to necessary resources and coordinate with the "Kolin Gjoka" school and Regional Labor Office in Lezhe to ensure smooth execution of the training activities.

Budget and Payment Schedule

- Interim Payment: 60% of the total budget upon successful completion of 3 training components (crafts, local producers and entreprenurship), including delivery of training materials, attendance records, and initial evaluation results.

- Final Payment: 40% of the total budget upon submission and approval of the final report, including performance evaluations, complete documentation, and recommendations for financial support scheme referrals.

*Required Qualifications and Experience

1. Craft Skills Trainer (Artisan Expert)

- Educational Background:

  - Vocational degree or diploma in Arts, Crafts, Textile, Design, or related field

- Professional Experience:

  - Minimum 3 years of proven practical experience in traditional craft production (e.g. textile weaving, embroidery, folk costumes or related artisan crafts), with demonstrated application of market-oriented designs.

  - Previous experience delivering hands-on, on-the-job training to adult learners, preferably women and/or rural artisans, using learning-by-doing methodologies.

  - Proven ability to integrate traditional craft techniques with contemporary design trends and basic market requirements (functionality, quality, usability).

  - Experience in preparing simple training plans, supervising use of materials, and documenting training results, including attendance records and brief technical reports.

2. Local Production Trainer

- Educational Background:
Degree or diploma in Agriculture, Food Technology, Agro-Processing, or related field

- Professional Experience:

  - Minimum 3 years of hands-on experience in olive and/or olive oil processing, including preservation, bottling and basic quality control.

  - Demonstrated experience in delivering practical, facility-based training to small-scale producers or farmers.

  - Knowledge of basic hygiene, food safety and product quality standards relevant to small and medium local producers.

- Marketing (local products) expert

- Educational Background:

  - Degree or diploma in Marketing, Business Administration, Economics, or related field

- Professional Experience:

  - Minimum 3 years of experience in marketing of agricultural or local food products, preferably working with small producers.

  - Proven experience in training or coaching producers on basic marketing concepts, labeling, packaging, pricing and market positioning.

  - Ability to deliver applied, practical marketing guidance adapted to local markets and low-scale production contexts.

- Entrepreneurship Trainer / Business Mentor

- Educational Background:

  - Degree in Business Administration, Management, Economics, or related field

- Professional Experience:

  - Minimum 3 years of experience in entrepreneurship training, business development services and/or mentoring of micro and small enterprises.

  - Proven experience in delivering business plan training and providing one-to-one mentoring support to start-ups or informal businesses.

  - Demonstrated ability to guide beneficiaries through early-stage business formalisation, costing, pricing and basic financial planning.

- General Requirements for All Trainers

- Strong facilitation and communication skills.

- Ability to motivate and engage adult learners.

- Capacity to adapt content to the needs of participants

- Ability to deliver training in Albanian (spoken and written).

- Strong documentation and reporting skills.

- Commitment to deadlines and professionalism.

- Ability to coordinate with WVA, NAES, and local business actors.

- Must comply with World Vision Albania's Child Protection Policy and sign the Code of Conduct.

- No involvement in unresolved legal disputes over the last three years (evidence required).

Administrative Arrangements / Ethical Standards

- Experts must declare any potential conflict of interest related to participant selection or grant application processes

- Any replacement of key experts must be approved in writing by WVA and meet the same qualification criteria.

Proposal/Documents and Expert Criteria Required for Submission

Please submit the following documents:

- A clear proposal framework explaining methodology and approach focusing on exploring the topics under the section responsibilities and deliverables. This document should be a descriptive framework of how the expert/s envision the process suggested in the ToR and division of the working days as per this ToR requisition in the excel document embedded below:

- An expression of interest for the consultancy;

- CV and Portfolio: Demonstrating relevant work experience.

- References: At least one reference from previous relevant projects and/or engagements.

- The consultancy fee should be inclusive of all applicable taxes, as detailed in the Financial Offer

- Must be cleared of legal disputes that ended in Court in the past three years. (e –Albania) (Deshmia e penalitetit);

- Sign the Supplier Code of Conduct;

- References and/ or sample of similar works

- If you are a registered company / organization / agency, please also provide:

  - Tax Registration number (NIPT)

  - Updated Extract generated from the National Registration Centre (QKR)

  - Provide last two years of audited financial statements or tax filing, or similar documents

Upon receipt of the application, World Vision will conduct a thorough due diligence process to evaluate the partner's capacity, credibility, and alignment with World Vision's mission and values. Only upon successful completion of this process will the contract be considered for signing.

General administrative information:

Technical proposal

In this part, the applicants will describe the approach and methodology for implementing the tasks. The proposal will include a statement outlining the rationale for the number and relevant experience of the experts/ agency that will be included for the service. If more than one expert will apply, team composition and distribution of tasks should be a specific section of the technical proposal.

Financial Proposal

The applicants should provide a detailed budget for delivering all the tasks and activities foreseen in this call. The budget should, include within the working days (fee days), all miscellaneous costs related with the preparation, presentation and printing of the final report.

*World Vision Albania maintains the confidentiality of the offer and documentation you submit based on its strict procurement policies.

Final Evaluation and Award of Contract

The contract will be awarded to the best technically acceptable proposal considering proposed prices.

The following formula will be used for combined technical and financial evaluation of proposals:

The lowest evaluated Financial Proposal (Fm) is given the maximum financial score (Sf) of 100. The formula for determining the financial scores (Sf) of all other Proposals is calculated as following:

Sf = 100 x Fm/ F, in which “Sf” is the financial score, “Fm” is the lowest price, and “F” the price of the proposal under consideration. The weights given to the Technical (T) and Financial (P) Proposals are:

T = 80, and P = 20

Proposals are ranked according to their combined technical (St) and financial (Sf) scores using the weights (T = the weight given to the Technical Proposal; P = the weight given to the Financial Proposal; T + P = 1) as following: S = St x T% + Sf x P%.

Only Bidders that have passed the pre-qualification process of Technical and Administrative proposals will be considered for financial proposal evaluation.

Selection process

The proposals received will be evaluated according to the following criteria:

1. Organization and Methodology (30 points maximum)

- Relevance and clarity of the proposed methodology for training and mentoring (10 points)

- Appropriateness of strategy for practical, on-the-job training and mentoring (10 points)

- Training strategy, structure of modules, and learning-by-doing approach (5 points)

- Realism and quality of activity timeline, including deliverable deadlines (5 points)

2. Qualifications and Experience of Key Experts (40 points maximum)

- Craft Skills Trainer / Artisan Expert (10 points)

- Local Production Expert – Olive/Oil Processing (10 points)

- Marketing Expert for Local Products (10 points)

- Entrepreneurship Trainer / Business Mentor (10 points)

3. Institutional / Individual Capacity (20 points maximum)

- Relevant track record and similar assignments completed in craft, local production, or entrepreneurship training (10 points)

- References and past performance (5 points)

- Capacity to manage logistics, participant coordination, and reporting (5 points)

Deadline for receipt of applications:

January 31, 2026

Questions/requests should be made by latest January 30 _________, 2026 to the following e-mail address: vangjel_kojku@wvi.org

Notes related to World Vision Albania Child Protection Policy:

All people working for World Vision Albania, or visiting its programmes are obliged to sign its Child Protection Policy and Behavior Protocols. This policy aims to create a child-safe organizational environment and is based on the principles of the UN CRC and its protocols. Important note: The contract will be awarded to the winner upon submission of official documents that certify that the full team of the project – including field team – complies with the child protection rules and procedures. The selected applicant will be informed about the required documents before finalization of the contract.

Principles of child protection involve briefly but are not limited to:

- Treat children with respect and dignity

- Listen to children views and opinions

- Inform children parents/legal guardian/s and take a written consent before any interaction with children (this involves special written permission when it comes to photographs/videos)

- Be sensitive to the child age and maturity, cultural background and local social and family norms and respect them

- Dress in culturally appropriate way.

- Always be in the company of another adult (preferably parent/legal guardian or teacher) when meeting a child

- All visitors to WVA projects must be in accompany of WVA staff.

- Do not abuse with children (sexual, emotional, psychological and physical abuse).

*Please note that World Vision Albania personnel and visitors are expected to report any suspicions of child abuse to the National Director immediately. WVA has policy and procedures that respond to accusations, which allows for a process that respects all involved. World Vision Albania holds the position that adults are always responsible for their behavior with a child, even if a child is acting seductively.